## Progress Summary
Work progress | Status | Date | Comments
Initial Deepak Discussion | Done | 2016-06-03
Initial Boobalan Discussion | Done | 2016-06-06
Intial Vishnu Discussion | Pending
Deepak plan review | Pending
Boobalan plan review | Pending
Vishnu plan review | Pending
Rahman plan review | Pending

## Pending Answers
Outstanding item from Front office
List of Service invoked directly from ATG CSC to OMS
List of Service invoked from ATG Website to OMS
List of Service invoked from IL to OMS
How to map GM lower environments to Platform environment - we just have 3 environment in platform but GM world we do have more that 4
SDC & WDC in Platform is it working fully?

## Plan
| Steps | Task | Owner | Date
| 0 | Provide the new wsdl to CSS, IL, Website | OFS
| 0.a | Consumers need to make appropriate code change to point to new wsdl for list of services The calls to the service which are not migrated should still go to GM OMS 8.0 vip | GM FO
| 0.b | Requesting system need to raise Infra request to open firewall across environments So that requestion system will talk to provider | GM FO
ATG CSC | 1 | For ATG CSC direct GM OMS 8.0 intraction
| 1.a | Take one of the server out of service in SDC - need manaul effort to perform this task | FO CSC
| 1.b | Deploy the change in one particular CSC server which is out of service in SDC | FO CSC
| 1.c | Make sure changes are deployed into CSC SDC server which is out of service | FO CSC
| 1.d | Test whether the call intiated by the the CSC SDC server via new wsdl - with new SDC vip (for a service which is migrated) is successful | FO CSC/OFS
| 1.e | Test whether the call initiated by the CSC SDC server via old wsdl (for non migrated service) is successful as well | FO CSC/OFS
| 1.f | If any of the above 2 steps fails, nail down the issue and fix it. If it is a code change then revert back to previous version | FO CSC/OFS
| 1.g | If both are successful, then propage the change across the cluster SDC - complete deployment flow | FO CSC
| 1.h | Perform sanity check post the code rollout to SDC servers and make sure no errors thrown because of network connectivity or high latency etc., | FO CSC
| 1.i | Repeat the step 1.a to 1.i for WDC CSC servers | FO CSC
ATG IL | 2 | For the calls through IL from ATG Website to GM OMS 8.0
| 2.a | Point all the trafic from ATG Website and ATG CSC to WDC
| 2.a | Take SDC out of service - (for now it is SDC) | FO IL
| 2.b | Deploy the changes in SDC IL servers | FO IL
| 2.c | Point one of the LSF to SDC | FO Web
| 2.d | Make sure changes are successsfully deployed into all SDC IL servers and one LSF is pointing to SDC IL | FO Web
| 2.e | Test whether the call intiated by one of the LSF server via SDC IL having new wsdl - with new vip (for a service which is migrated) is successful | FO Web
| 2.f | Test whether the call initiated by one of the LSF server via old wsdl (for non migrated service) is successful | FO Web
| 2.g | If any of the above 2 ssteps fails, nail down the issue and fix it. If it is a code change then revert back to previous version | FO Web
| 2.h | If it is success, then propage the changes across all the LFS servers to point all the traffic through SDC IL | FO Web
| 2.i | Perform sanity check after pointing all the LSF servers to SDC and make sure no errors thrown because of network connectivity or high latency etc., | FO Web
| 2.j | Deploy the change in WDC IL servers | FO IL
| 2.k | Point one of the LSF to WDC | FO Web
| 2.l | Make sure changes are successsfully deployed into all the WDC IL servers and one LSF is pointing to WDC IL | FO Web
| 2.m | Test whether the call intiated by one of the LSF server via WDC IL having new wsdl - with new vip (for a service which is migrated) is successful | FO Web
| 2.n | If it is faliure, nail down the issue and fix it | FO Web
| 2.o | If it is success, then propage the changes across all the LFS servers and balance the traffic through WDC IL | FO Web
| 2.p | Perform sanity check post the code rollout and make sure no errors thrown because of network connectivity or high latency etc., | FO Web